| DEPARTMENT OF HEALTH SERVICES Division of Quality Assurance F-00176 (08/2017) |  |  |  |  |  |  |  | STATE OF WISCONSIN Page 1 of 4 |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CIVIL MONEY PENALTY FUNDS PROJECT PROPOSAL |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| For Stakeholders of Federally Certified Nursing Facilities and Skilled Nursing Facilities Applying for Use of Civil Money Penalty Funds |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| INTRODUCTION This project proposal form is an application for grant monies derived from Civil Money Penalty (CMP) funds. Grants are available for projects or programs that are provided through various stakeholders, e.g., federally-certified skilled nursing facilities (SNFs) and nursing facilities (NFs), consumer groups, professional nursing home associations, advocacy groups, quality improvement organizations. Note: These grants are not available to state-licensed only nursing facilities or stakeholders. The Quality Assurance and Improvement Committee (QAIC) reviews all proposals. The QAIC is the sole judge as to compliance with the requirements contained in this form. The QAIC retains the right to accept or reject any or all proposals or to accept or reject any part of a proposal. Proposals which do not comply with instructions or are unable to comply with specifications mandated by the QAIC may be rejected. The QAIC may request reports regarding the financial stability of an applicant and, if financial stability is not substantiated, may reject the proposal. Recipients of awards will be required to make project reports to the QAIC at least every three months unless, based upon the nature of the project, the QAIC decides otherwise. For more information regarding these grants and the QAIC, see DQA publication P-00422, Quality Assurance and Improvement Committee, and visit https://dhs.wisconsin.gov/regulations/qai/introduction.htm . Questions may be addressed to the Division of Quality Assurance at 608-266-8481. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| FUND RESTRICTIONS Below is a list of restrictions received from the Centers for Medicare and Medicaid Services: - Lodging (Allowable) Lodging to attend a training or conference is allowable, as long as the attendee lives at least 50 miles away and the conference is longer than one day. - Travel (Allowable) - Travel for a contractor to visit multiple facilities to conduct training - Travel reimbursement for nursing home staff to attend training or a conference - Travel of nursing home staff who have become “Train the Trainers” to travel to other sites and conduct training - Food – Per diem (Not Allowable) - Food is an expense that is not allowable under the CMP Use Program. - Per diem must be broken down so that travel, lodging, and food are separated and food can be excluded. - University Health and Human Services Rate Agreements If a proposal is submitted by a university and includes fringe benefits and facility and administrative costs for university staff, the university must include a copy of their department of health and human services rate agreement. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SUBMISSION INSTRUCTIONS - Requests will NOT be accepted via facsimile or mail. All requests must be submitted electronically to: dhswebmaildqa@wisconsin.gov In “Subject” line, enter: ATTN: Quality Assurance and Improvement Committee - All applicants must submit their request using DQA form F-00176, Civil Money Penalty Funds Project Proposal. 3. Requests shall include a cover letter addressed to the Quality Assurance and Improvement Committee. 4. The font for all CMP requests is Times New Roman, 12 point. The entity name, project title, and page numbers must be present on all documents. 5. Request should be limited to no more than 10 pages, including appendices and the actual request form (DQA form F-00176, CMP Funds Project Proposal). Pages should not include color background, photos, or illustrations (as are often found in PowerPoint presentations). 6. When CMP funds are requested for educational purposes, the applicant must also include: - Anticipated number of attendees - Target audience - Accrediting authorities - Time-line for implementation - Plan for sustainability - Letters of support Representatives from any group requesting funding or representatives who are in situations where a conflict of interest exists, must disqualify themselves from making recommendations. (Continued on page 3) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| GENERAL INFORMATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Title – Project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Name – Applicant (Submitting Organization) |  |  |  |  |  |  |  |  |  |  | Tax ID No. (FEIN) |  |  |  |  |
| Mailing Address – Street Address or P.O. Box |  |  |  |  | City |  |  |  |  | County |  |  | State |  | Zip Code |
| Name – Project Contact |  |  |  |  |  |  | Title – Project Contact |  |  |  |  |  |  |  |  |
| Telephone No. |  |  |  |  |  | Email Address |  |  |  |  | Date Submitted (MM/dd/yyyy) |  |  |  |  |
| SIGNATURE – Project Originator |  |  |  |  |  |  |  |  |  |  | Date Signed (MM/dd/yyyy) |  |  |  |  |
| PROJECT DETAILS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The following items are expandable. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1. Summary of the Project and its Purpose. Provide a summary of the project. List the (a) problem or gap this project is aiming to address, (b) goals and/or objectives, and (c) a plan to implement the project to include a timeline. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A) Seniors who live in residential assistance homes are at risk of experiencing loneliness. Loneliness can lead to social isolation which negatively impacts an individual’s health and well-being. Social isolation can hinder cognitive growth and lead to depression in residents, ultimately worsening their quality of life. Interventions, like TimeSlips, have been utilized to address social isolation in nursing homes. Seniors who participate in programs like TimeSlips are less likely to experience loneliness, which improves their quality of life. B) Our project's goal is to improve the quality of life for Fair Haven residents by reducing loneliness and social isolation. We will accomplish this by implementing a TimeSlips program between residents and UW-Whitewater students enrolled in a community-based learning course. Designated Fairhaven staff will train the students in TimeSlips. Then the students will facilitate the TimeSlips with the residents. C) The plan to implement this project involves capitalizing on a partnership between Fairhaven Seniors Services and the University of Wisconsin-Whitewater (UW-W). Staff at Fairhaven will train students to work with the Fairhaven residents who live on the skilled nursing floors. To prepare students to engage with the residents, students will receive education on aging and social isolation among older adults– including curriculum on the negative health effects of social isolation and ways to improve it. Educational instruction will be co-delivered by UW-W faculty and Fairhaven staff. As part of the class, students will receive training on TimeSlips. TimeSlips training will be completed online and supplemental instruction will be provided by the Fairhaven staff who are certified as master trainers. Once students complete the TimeSlips training, they will implement and deliver the intervention at Fairhaven for a period of 10 weeks to residents who live on the skilled nursing floors. At the beginning of the program, the residents will complete a survey indicating levels of loneliness that they are experiencing. After the 10 weeks has been completed, the residents will respond to the survey questions one last time to convey the effect of TimeSlips on their loneliness. For timeline see appendix, item 1 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2. Unique / Innovative. Briefly describe how your proposal is unique and innovative and how it is relevant to the improvement of quality of care / life for residents in Wisconsin nursing homes. Append any supportive research or literature. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| This proposal is unique because it provides the residents with a structured interaction with younger generations that can be sustained through UW-Whitewater's community-based learning course. Seniors living in residential assistance homes are at risk of experiencing social isolation. Social isolation has negative impacts on an individual's cognitive growth, health, and well-being. Activities like TimeSlips are designed to improve residents' cognitive ability, promote social interaction, and encourage self-integration. The students are a key component in this exercise because the interaction with them can enhance the residents' quality of life "by acting on their emotional realm and residual relational capabilities" (Santini et al. 2018). It has been observed that interventions like TimeSlips can also help prevent depression as Chiang noted that "the group process of sharing and praising each other often brought cohesion and friendship to these elderly residents, which significantly improved their depressive systems" (et al. 2010). As social isolation among residents decreases, so will prescribed psychotic medications which will improve their well-being overall. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3. Expected Outcomes. Describe the intended outcomes and sustainability of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| There are two expected outcomes in this project. 1) To reduce loneliness among residents of Fairhaven 2) To increase intergenerational interactions In terms of resources, the project is sustainable in that there will always be students available to facilitate the TimeSlips at Fairhaven. To sustain the project beyond the funding period, we will organize the events described below. A) 5K Fundraiser: This will be put on with the help of UW-Whitewater Greek Life. Greek organizations are constantly seeking creative ways to fulfill service hours so they will be willing to volunteer to staff this event for our cause. We will request donations from local businesses in exchange for advertising space on a t-shirt and signs posted about the event. Another positive takeaway from the 5K is that the families of the residents can participate in it too. The 5K fundraiser is a fun and friendly way to make the public aware of our project. B) Cookie Sales: This simple fundraiser can easily turn a profit with little cost to us. We can sell the cookies at a table in the University Center during the winter months. This will also help create awareness of our project among the university community. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4. Deliverables. Provide a detailed, numbered list of the project deliverables. Include all components of the project, such as planning, implementation, and evaluation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) Implement community based learning course at UW-W: At least 12 students will enroll in the course. Course materials will be prepared to give to students when classes start in September. 2) Train staff at Fairhaven in TimeSlips: At least 1 staff member will be trained as a Master Trainer for TimeSlips by mid-September. 3) Train students in TimeSlips: Master Trainer at Fairhaven will train the students on how to do TimeSlips with the residents. This will be completed by the beginning of October. 4) Measure loneliness for Fairhaven residents: Fairhaven residents will be surveyed using the UCLA Loneliness Survey prior to starting TimeSlips and after finishing the program. The first survey will be taken in October and the last survey will be taken in December. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5. Scope of Work. Provide a detailed, numbered list of the intended scope of work. Include all components of the project, such as planning, implementation, and evaluation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 1) Reduce loneliness among Fairhaven residents: The TimeSlips program will be utilized bi-annually to encourage residents to interact with each other and with students from UW-Whitewater. The intended timelines will provide one session from September through December, and one from January through May. To determine if the program resolves loneliness within Fairhaven residents, a pre-post program survey will be evaluated after each session. 2) Increase structured intergenerational interaction: The residents will work on TimeSlips with students from UW-Whitewater who are enrolled in a community-based learning course. The course will ensure that the program continues bi-annually in accordance to the university's semester schedule. The timeliness of this program will increase intergenerational interactions because a new group of students will be cycled through the course each semester. The residents will have more opportunities to connect with the younger generation in a structured environment. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6. Documentation of Results. Explain how the information from the results of your proposal will be gathered and evaluated. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The residents will fill out a pre-post program survey to determine levels of loneliness. This information will be used to determine how effective the TimeSlips program will be for reducing loneliness for residents in assisted living homes. Dr. Yeongmin Kim, a UW-W associate professor of social work, will evaluate the surveys for any change in responses from the beginning to the end of the program. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7. Results Measurement. Describe the methods by which the project results will be assessed. Include specific measures. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The UCLA Loneliness Scale is considered to be a consistent psychometric analysis in evaluating an individual's loneliness. Through compiling the results from this survey during the granting period, we can determine whether participating in TimeSlips with university students is a success in reducing loneliness among residents at Fairhaven. This will be done by evaluating the change in responses from the residents prior to the program starts and after the program has finished for every session. For survey see appendix, item 2. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8. Non-Supplanting. Describe the manner in which the project will not supplant existing responsibilities of the facility to meet current Medicare/Medicaid requirements or other statutory and regulatory requirements. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9. Qualifications. Describe how your organization is qualified to carry out the proposal. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The University of Wisconsin - Whitewater has an established relationship with Fairhaven. Faculty from both institutions have collaborated throughout the years to create a community between the students at the university and the residents at Fairhaven. Dr. Jeannine Rowe, the instructor of the community-based learning course at UW-W, is an associate professor in the Social Work degree program. Dr. Rowe has teamed up with Fairhaven's Director of Leisure Services, Brian Robinson, to introduce the TimeSlips program to Fairhaven residents in the Fall of 2019. Brian and Dr. Rowe's efforts were supported by the Bader Grant which helped fund the initial startup for this project at the facility. These continued partnerships between the faculty at Fairhaven and UW-W will ensure that the residents at Fairhaven will be able to participate in programs, like TimeSlips, for years to come. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10. Consumer and Other Stakeholder Involvement. Describe how the facility community, including resident and/or family councils and direct care staff, will be involved in the development of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11. Involved Organizations. List all organizations (names and addresses) that will receive funds through this project. Also, list sub-contractors and organizations that are expected to execute and bear responsibility for components of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12. Other Funding Sources. If other funding sources have been applied for and/or granted for this proposal or project, explain and identify sources and amounts. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13. Funding. Provide the specific amount of CMP funds requested, an itemized budget to be used for this project, and an estimate of any non-CMP funds that the State or other entity are expected to contribute to the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14. Time Period. Provide the time period of the project. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| No. of Years: |  | Specific Dates Proposed for the Project – From: |  |  |  |  |  |  |  |  | To: |  |  |  |  |
| ATTESTATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| The applicant attests that all statements made and information provided on the Civil Money Penalty Funds Project Proposal are true and correct. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| SIGNATURE – Applicant |  |  | Name – Applicant (Print or type.) |  |  |  |  |  |  |  | Date Signed |  |  |  |  |